## Cover
April 2025 Court Paper - Action Plan
Version Control | 2025-05-15 | FOI Status: Open
Colour Key:
Too soon to report
Lagging
On Track
Action complete

## Action Plan
Action | Key Activities | Lead Responsibility | Working With | Timeline | Progress | Status
Development of Implementation Plan
Proposal considered by SMT | Implementation Plan drafted and endorsed | Heather Crabb | Jo-Anne Murray Nick Edwards Fraser Bell Samantha Waters Ainhoa Burgos-Aguilera Graeme Kirkpatrick Christina Schmid | Paper submitted to meeting on 22 May 2025 | Draft Plan and cover paper circulated for comments 15 May | Actoin complete
Update provided to Assembly delegates | Message drafted and circulated | Heather Crabb | Jo-Anne Murray Nick Edwards Fraser Bell Samantha Waters Ainhoa Burgos-Aguilera Graeme Kirkpatrick Christina Schmid | Message issued following SMT meeting on 22 May 2025 | Message issued 6 June 2025 | Action complete
Consultative Structure & Process
Responsibility for overseeing the Assembly Implementation Plan assumed by Equality, Diversity & Inclusion Committee (EDIC) | EDIC invited to amend its remit to assume responsibility for overseeing the Assembly Implementation Plan | Jo-Anne Murray | Nick Edwards Ainhoa Burgos-Aguilera | Paper submitted to meeting on 2 July 2025 | Paper circulated to EDIC (meeting cancelled) but comments invited via circulation Action plan endorsed at September meeting | Action underway
Establishment of Task & Finish Group (EDIC members and other staff/students on ex officio basis) to develop a Framework/Guiding Principles to underpin a consultative structure and process within which dialogue can take place and decisions taken on (i) which conflicts University will respond to, and (ii) form of support that could be offered | TFG established by EDIC and invited to (i) develop its remit/composition and (ii) identify staff/student members outwith the Committee as appropriate | Jo-Anne Murray |  | First meeting of Group by October 2025 | Terms of Reference approved by EDIC at September meeting
Framework/Guiding Principles developed and approved by EDIC | Plan of work established by TFG to identify key themes for inclusion in the Framework/Guiding Principles, including suggestions arising from Assembly: | Jo-Anne Murray (TFG) |  | Plan of work established November 2025
| • Existing groups/ongoing activities across various areas collated and incorporated in the Framework/Guiding Principles to encourage more coherent and integrated ways of working; | TFG | See actions below (Provision of Practical & Educational Support) | See action below
| • A consultative process developed to support the drafting of future communication messages | TFG | See action below (Institutional Communications) | See action below
| • Consideration of whether alignment to United Nations and other recognised international norms of terminology when drafting public statements and student/staff communication messages might be helpful | TFG | Jen Phillips Nick Edwards SA Communications Team | TBC by Framework/GPs timeline
| • Drafting of FAQs or other guidance outlining statutory and external limitations on what the University can offer students and staff e.g. immigration status, travel, family members etc. | TFG | Nick Edwards Fraser Bell Relevant PS Leads SA team | TBC by Framework/GPs timeline
| Framework/Guiding Principles drafted and considered by EDIC | TFG |  | Draft Framework considered by EDIC by December 2025
Establishment of Incident Response Group (mirroring existing processes, but focus as determined by the Framework/Guiding Principles) | Establishment of a 'rapid reaction' group (including relevant University and SA staff) that can be stood up quickly in the event of a situation arising to collaboratively engage on the University's response to situations including (but also beyond) international conflict e.g. natural disasters, terrorist events etc. | Nick Edwards Graeme Kirkpatrick | Fraser Bell Jen Phillips Relevant PS Leads SA team | Group established by July 2025 (remit to be agreed at first meeting)
Institutional Communications
Establishment of an agreed programme of educational sessions on relevant topics to enhance awareness of international conflict issues and encourage cultural tolerance/understanding on campus | Reach agreement on a list of appropriate external speakers/internal colleagues to deliver eduational sessions on relevant topics | Jo-Anne Murray | Relevant Academic areas and external individuals/organisations as appropriate | Programme established for implementation during Session 2025/26 | Positive feedback was received on the educational sessions delivered after the Assembly around terminology in the context of the Israel/Palestine conflict
| Suggested programme of events for Session 2025/26 presented to EDIC for consideration | Jo-Anne Murray |  | November 2025 meeting
Consider a revised way of drafting communication messages when a stuation requiring a 'rapid response' arises | Consider how we can implement a more consultative process in drafting communication messages | Nick Edwards Jen Phillips | Jen Phillips SMT SA Team | Implementation TBC by establishment of Rapid Reaction Group
Provision of Practical & Educational Support
Collation of existing disparate (and identification of other) practical support provisions into a coherent institutional support package which could be offered in conflict situations |  | Nick Edwards Christina Schmid | PS Leads SA Team SAMs | 2025-12-01 | Assembly suggestions included: • support for refugees and asylum seekers in local community e.g. clothes, bedding, tosy • legal and other professional support to refugees and asylum seekers from colleagues in relevant disciplines • awareness raising activities for areas experiencing conflict e.g. guest speakers, honorary degrees • promotion and provision of counselling and mental health support • recognition of impact on e.g. mitigating circumstances/special provisions in coursework
Collation of existing disparate (and identification of other) educational support provisions into a coherent institutional support package which could be offered in conflict situations |  | Jo-Anne Murray Christina Schmid | Heads of School Global Engagement, Marketing & Recruitment Team | 2025-12-01 | Current provisions include: • At Risk & Displaced Person Scheme • Library materials •online courses •scholarships Assembly suggestions: • in-country scholarships • partnership activities with organisations in affected regions to provide educational support
Policies & Partnerships
Review Procurement Policy in line with normal practice and in the context of Assembly discussions | Chief Financial Officer invited to review Policy in line with normal policy review practice and present for University consideration via the internal governance structure - including consideration of its wider implications and implementation e.g. Investment Policy/divestment decisions, invitations extended to organisations to campus events including Careers Fairs etc. | Mark White Christina Schmid | PS Leads SA Team | 2025-12-01
Leadership Role
Review the decision to pause the institutional application to become a University of Sanctuary | Undertake review in liaison with relevant colleagues and present findings to SMT for consideration | Fraser Bell | University of Sanctuary Group | Recommendation presented to SMT October 2025
Communication Strategy
Embed the communication plan relating to the Implementation within EDIC's existing mechanisms and planning processes for communications and events | Develop Communication Plan/key communications activities | Jo-Anne Murray | Jen Phillips SA Team | Communications embedded in EDIC plans following September 2025 meeting
| Monitor progress as part of EDIC monitoring process | Jo-Anne Murray |  | Timeline to be agreed by EDIC
Monitoring & Evaluation
Establishment of an annual 'listening exercise' to enable staff and students to reflect on activities and progress (including and beyond topics considered by the Assembly). | Annual 'listening exercise' designed and delivered to demonstrate how the conversation and engagement process started by the Assembly is being built upon | Jo-Anne Murray |  | First exercise scheduled to take place in March 2026 (to inform the Assembly review)

## Communications (hidden)
FRP Ref | Action Ref | Aim | Action | Lead Responsibility | Working With | Timeline | Progress | Status
|  | Identify innovative income generation ideas, establish a process for considering suggestions and monitor outcomes | Issue a call for income generation suggestions via Ezine | Project Manager |  |  |  | Action Completed
|  |  | Report ideas taken forward and levels of income generated as part of FRP monitoring | Project Manager |  |  |  | Action Completed
|  | Establish Implementation Group website | Move current Open Session information from Events page to a new section | Associate Director of Public Affairs | Head of Communications Project Manager | 2024-04-01 |  | Action Completed
|  |  | Update content to include tabs for staff communication messages | Associate Director of Public Affairs | Head of Communications Project Manager | 2024-04-01 |  | Action Completed
|  | Establish branding for FRP messaging | Mock-ups of IG branding and broader R2R branding to be approved by IG | Associate Director of Public Affairs | Head of Communications Project Manager | 2024-04-01 |  | Action Completed
|  | Engage with MSP/MP stakeholders | Establish political engagement plan | Associate Director of Public Affairs | Head of Communications Project Manager | 2024-10-01 | Meetings and communications for strategic engagement with ministers, MPs and MSPs is well established | Action Completed
|  | Analyse external media coverage statistics/reputational/'sentiment' measures | Establish process for monitoring external media coverage | Associate Director of Public Affairs | Head of Communications Project Manager | 2024-12-01 | Capability of current media monitoring software being explored | Action Completed
|  |  | Establish reporting process for outcomes/analysis | Associate Director of Public Affairs | Head of Communications Project Manager | 2025-01-01
|  | Establish a schedule of weekly Implementation Group communication topics to reflect key workstream priorities | Establish schedule and keep under regular review as a standing item on IG agendas | Project Manager | IG | 2024-05-01 | Weekly staff messages being issued | Action Complete